# Bachelor Thesis Roadmap

Structural Knowledge Integration in Data-Driven Predictive Control

### Ahmed Tarek El Hossainy

RWTH Aachen University Last Updated: March 24, 2026

## Thesis Progress & Milestone Tracker

| Week | Phase | Core Objective | Status |
| --- | --- | --- | --- |
| 1 | Setup | System Architecture & Data Generation | Completed |
| 2 | Phase 1 | DPC Deconstruction & Structural Lifting | In Progress |
| 3 | Phase 1 | Residual Learning & MPC-DPC Hybridization | Remaining |
| 4 | Phase 2 | Hammerstein-Wiener Nonlinear Block Implementation | Remaining |
| 5 | Phase 2 | Data Lifting & Kernel Learning Exploration | Remaining |
| 6 | Phase 2 | Stability Analysis & Regularization Tuning | Remaining |
| 7 | Phase 3 | Online Data Selection (Select-DPC) | Remaining |
| 8 | Phase 3 | Contextual Sampling for Nonlinear Trajectories | Remaining |
| 9 | Phase 3 | Comprehensive System Stress Testing | Remaining |
| 10-12 | Phase 4 | Unknown / Research Expansion | Remaining |

## Phase 1: Code Ownership & Structural Foundations

### Week 2: DPC Deconstruction & Structural Lifting (Current)

Started: March 18. Goal: Bridge the gap between AI-generated code and proprietary under-standing.

  - Code Refactoring: Deconstruct the existing DPC setup. Manually rebuild the block Hankel matrix H to understand the time-shifted trajectory representation and its reliance on the fundamental lemma.

  - Manual Lifting: Implement structural transformations derived from the kinematic bicy-cle model. Specifically, map the steering angle δ → tan(δ) to linearize the yaw dynamics.

  - Linearization with DPC: Evaluate if the transformed data makes the system more amenable to the linear assumptions of the DeePC framework.

  - Deliverable: A proprietary, line-by-line understood DPC engine with manual input lift-ing.

### Week 3: Residual Learning (MPC-DPC Hybrid)

Goal: Using established MPC knowledge to master data-driven residuals.

  - Residual Framework: Deduce a nominal model from the kinematic bicycle physics (as used in the MPC setup).

  - Identification of Error: Measure real simulation trajectories and compute the ”Predic-tion Gap.” Configure the DPC to predict only this residual error.

  - Error Correction: Use the Hankel matrix to learn the prediction error of the nominal model, rather than the full state, increasing robustness against nonlinearities.

  - Deliverable: A functional ”Residual-DPC” script where the nominal model handles the base physics and DPC handles the unmodeled dynamics.

## Phase 2: Complex Transformations & Stability

### Week 4: Hammerstein-Wiener Nonlinearities

  - Implementation: Model the system as a linear block ”sandwiched” between static non-linearities. Apply the Hammerstein function to describe input nonlinearities before they enter the DPC solver.

### Week 5: Advanced Data Lifting & Kernels

  - Kernel Learning: Explore lifting the data into higher-dimensional spaces using basis functions or kernels to capture dynamics that manual lifting might miss.

### Week 6: Stability & Regularization

  - Theoretic Rigor: Study and implement ℓ1 and ℓ2 regularization on the weight vector

g. Incorporate terminal constraints to provide theoretical stability guarantees for the transformed setup.

## Phase 3: Real-Time Optimization & Selection

### Week 7: Online Data Selection (Select-DPC)

  - Dynamic Data: Implement nearest-neighbor column selection (Näf 2025). Construct miniature, localized Hankel matrices on the fly to improve real-time performance.

### Week 8: Contextual Sampling

  - Reference Awareness: Implement contextual sampling (Beerwerth 2025) to select his-torical data based on the intended future reference trajectory rather than just the current state.

### Week 9: Benchmarking & Stress Testing

  - Evaluation: Run rigorous comparisons between the [Nominal MPC], [Vanilla DPC], and [Structure-Informed DPC] across extreme curvatures and noise profiles.

## Phase 4: Unknown

  - TBD: Research expansion based on Phase 3 results, thesis documentation, and project synthesis.